Software Development & Engineering  ·  Since 1996

Proposal Prepared For

Kash Kids

Unified Franchise & Education

Management Platform

Web Platform  ·  Mobile Apps  ·  AI-Powered Analytics

Version 1.0          Date: 28 May 2026

Confidential — for the addressed recipient only

# Table of Contents

1.   Executive Summary	3

2.   Our Understanding of Your Requirement	3

3.   Why Partner With Us	4

4.   Project Objectives	4

5.   Scope of Work	5

6.   Value-Added Features (Included)	7

7.   Technical Architecture	8

8.   Effort Estimation	8

9.   Resource Allocation	9

10.  Implementation Timeline	10

11.  Commercial Structure	10

12.  What’s Included & Out of Scope	12

13.  Assumptions	12

14.  Warranty & Support	12

15.  Next Steps	12

# 1. Executive Summary

Thank you for the opportunity to propose a technology partner for Kash Kids. This document sets out the scope, deliverables, architecture, timeline, and commercials for building a Unified Franchise & Education Management Platform that runs your entire network from a single system.

Kash Kids operates a growing preschool and abacus brand with two clear engines of growth: franchise expansion and teacher training. As the network scales, the operational load — onboarding new centres, tracking students across batches, collecting fees, certifying teachers, and keeping parents informed — quickly outgrows spreadsheets and disconnected tools. Our platform brings all of it into one place.

The platform is built to digitise and centralise:

- Franchise lifecycle — from lead to onboarding to ongoing governance

- Student lifecycle — registration, batch mapping, attendance and progress

- Learning, assessments and teacher certification

- Fee management and financial visibility across every centre

- Parent engagement and communication

- Compliance, quality and real-time analytics

It is delivered as a secure, multi-tenant system — each franchise sees only its own data, while head office gets a real-time view across the whole network. We deliver in two phases so you go live faster and pay in step with progress.

Headline commercials:  Total ₹6,40,000 (exclusive of GST). Sign both phases together and pay ₹6,10,000 — a ₹30,000 saving. Backed by a 90-day warranty and 30 days of free post-launch support.

# 2. Our Understanding of Your Requirement

Kash Kids is more than a single preschool — it is a brand built to be replicated. That shapes everything about the platform. The four programmes on your site (Preschool, Abacus, Franchise and Teacher Training) map directly to the modules we propose:

| YOUR BUSINESS AREA | WHAT THE PLATFORM DOES FOR IT |
| --- | --- |
| Preschool & Abacus (Playgroup, Nursery, Jr. KG, Sr. KG) | Student registration, batch and time-slot mapping, attendance, and program-specific progress tracking for each level. |
| Franchise expansion | Lead capture, multi-step onboarding with KYC and documents, territory mapping by city/pincode, and a live status dashboard per centre. |
| Teacher Training & Certification | Trainer onboarding, level-based training content, MCQ assessments, pass/retake logic and auto-generated certificates. |
| Parent trust & retention | A parent view of progress, attendance and fees, with timely alerts — reinforcing the experience your testimonials already speak to. |

In short: we are not proposing a generic ERP. We are proposing a platform shaped around how Kash Kids actually grows.

# 3. Why Partner With Us

| WHAT YOU GET | WHY IT MATTERS |
| --- | --- |
| Sharper commercials | ₹6,40,000 vs comparable market quotes around ₹7,10,000 — roughly 10% lower for the same (and broader) scope, with a bundle discount on top. |
| Longer warranty | 90 days of warranty cover after go-live, versus the 30 days commonly offered — three times the protection at no extra cost. |
| AI built in, not bolted on | Smart analytics, an admin/parent assistant chatbot, and at-risk-student insights are included in scope — not priced as extras later. |
| Source code ownership | On final payment, full source code and IP transfer to Kash Kids. No vendor lock-in. |
| Clear, milestone-linked payments | You pay as verified deliverables land, against a transparent change-request process for anything new. |
| Free training & documentation | Admin and franchise onboarding sessions plus written guides, so your team is self-sufficient from day one. |

# 4. Project Objectives

The platform will enable Kash Kids to:

- Digitise franchise onboarding and governance end to end

- Streamline the full student lifecycle and academic operations

- Run structured learning, assessments and teacher certification

- Improve fee collection and give head office real financial visibility

- Strengthen parent engagement and communication

- See real-time analytics across every franchise

- Scale franchise expansion without scaling the back-office headache

# 5. Scope of Work

## Phase 1 — Core Platform (Operations + Academic Foundation)

5.1  Franchise Management System

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Onboarding | Multi-step workflow | Franchise onboarding with KYC, business and infrastructure details |
| Document Management | File storage | Upload, versioning and approval/rejection |
| Approval System | Status flow | Draft → Review → Approved/Rejected |
| Territory Management | Mapping | City / pincode allocation to prevent overlap |
| Franchise Profile | Dashboard | Franchise details and live status tracking |

5.2 CRM & Lead Management

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Lead Capture | Manual + web form | Capture enquiry details from any source |
| Pipeline | Lifecycle | New → Demo → Converted / Lost |
| Conversion | Lead → Student | One-click conversion into student onboarding |

5.3 Student Information System (SIS)

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Registration | Student profiles | Personal and parent details |
| Enrolment | Course mapping | Batch and time-slot assignment |
| Attendance | Tracking | Batch-wise attendance capture |
| Dashboard | Student view | Progress and attendance at a glance |
| Progress Engine | Metrics | Program-specific tracking (preschool levels, abacus) |

5.4 Learning Management System (LMS)

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Course Management | Structure | Levels and modules |
| Content Management | Upload | PDFs, videos and documents |
| Access Control | Permissions | Student- and role-based access |
| Progress Tracking | Completion | Course completion tracking |

5.5 Teacher Training & Certification

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Trainer Management | Profiles | Trainer onboarding |
| Training Modules | Content | Level-based learning paths |
| Quiz Engine | Assessments | MCQ-based tests |
| Certification | Logic | Pass percentage and retake rules |
| Output | Certificate | Automatic PDF certificate generation |

5.6 Academic Assessment System

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Assessment Creation | Quiz setup | Admin-driven question setup |
| Execution | Timer-based | Auto-submission on time-out |
| Evaluation | Auto grading | Automatic score calculation |
| Reporting | Analytics | Student and batch-level reports |

## Phase 2 — Financials, Engagement & Community

5.7 Financial Management System

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Fee Configuration | Plans | Monthly / quarterly fee plans |
| Payment Tracking | Status | Paid / Pending / Overdue |
| Instalments | Tracking | Fee schedules and reminders |
| Dashboard | Revenue | Insights and analytics for head office |

5.8 Parent Engagement System

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Dashboard | Parent view | Child progress and attendance |
| Notifications | Alerts | Fee reminders and attendance alerts |

5.9 Community & Communication Platform

| MODULE | SUB-MODULE | FUNCTIONALITY |
| --- | --- | --- |
| Announcements | Role-based | Admin / Teacher / Franchise broadcasts |
| Moderation | Control | Approval and reporting workflow |

# 6. Value-Added Features (Included)

These are part of the proposed scope at no extra cost — they are where we go beyond a standard build:

| FEATURE | WHAT IT DOES |
| --- | --- |
| AI Insights Dashboard | Surfaces trends across centres — enrolment dips, fee defaults, attendance drops — so head office acts early. |
| At-Risk Student Alerts | Flags students whose attendance or progress is slipping, helping franchises improve retention. |
| Admin & Parent Assistant | An in-app chatbot that answers routine questions on fees, schedules and progress. |
| Role-Based Access Control | Granular permissions for head office, franchise owner, teacher, trainer and parent. |
| Audit Trail | Every key action is logged for compliance and dispute resolution. |

# 7. Technical Architecture

A modern, multi-tenant architecture with strict data isolation between franchises and a single source of truth for head office.

| LAYER | COMPONENT | TECHNOLOGY |
| --- | --- | --- |
| Frontend | Web platform | React / Next.js |
| Mobile | Apps (iOS + Android) | React Native |
| Backend | APIs & services | Node.js / NestJS / Python |
| Database | Storage | PostgreSQL |
| Infrastructure | Hosting | AWS + Docker |
| Security | Access | Role-based access + tenant data isolation |

# 8. Effort Estimation

Phase 1

| ACTIVITY | EFFORT (HOURS) |
| --- | --- |
| Platform setup | 150 |
| Franchise + CRM modules | 400 |
| SIS + LMS | 360 |
| Assessment + Teacher Training | 420 |
| QA & testing | 150 |
| Deployment | 100 |
| Project management | 120 |
| Total — Phase 1 | 1,700 |

Phase 2

| ACTIVITY | EFFORT (HOURS) |
| --- | --- |
| Financial system | 360 |
| Parent + engagement | 420 |
| Community / communication modules | 80 |
| Testing & deployment | 120 |
| Total — Phase 2 | 980 |

# 9. Resource Allocation

| ROLE | RESOURCES |
| --- | --- |
| Backend Engineer | 2 |
| Frontend Engineer | 1.5 |
| Native App Developer | 1.5 |
| QA Engineer | 1 |
| DevOps Engineer | 1 |
| AI Engineer | 1 |
| Project Manager | 1 |

# 10. Implementation Timeline

Phase 1 — 12 to 14 weeks

| ACTIVITY | START | END |
| --- | --- | --- |
| Discovery & architecture | Week 1 | Week 2 |
| Platform setup | Week 2 | Week 3 |
| Franchise + CRM modules | Week 3 | Week 7 |
| SIS + LMS | Week 4 | Week 9 |
| Assessment + Teacher Training | Week 6 | Week 10 |
| QA & testing | Week 10 | Week 12 |
| Deployment & go-live | Week 13 | Week 14 |

Phase 2 — 8 to 9 weeks

| ACTIVITY | START | END |
| --- | --- | --- |
| Financial system | Week 1 | Week 5 |
| Parent + engagement | Week 4 | Week 7 |
| Community / communication | Week 6 | Week 7 |
| Testing & deployment | Week 7 | Week 9 |

# 11. Commercial Structure

## 11.1  Phase-Wise Pricing

| COMPONENT | COMMERCIAL (₹) |
| --- | --- |
| Phase 1 — Core Platform Development | 3,95,000 |
| Phase 2 — Advanced Modules & Enhancements | 2,45,000 |
| Total Estimated Cost | ₹6,40,000 |

Bundle offer: commit to both phases at kickoff and the total is ₹6,10,000 — a saving of ₹30,000.

All figures are exclusive of GST. Third-party tools, integrations and hosting/infrastructure are billed at actuals or borne directly by Kash Kids.

## 11.2  Payment Terms & Milestones

Payments are phase-wise and milestone-linked, so they track delivery progress.

Phase 1 — Core Platform Development

| MILESTONE | DESCRIPTION | PAYMENT |
| --- | --- | --- |
| Milestone 1 | Post discovery, requirement finalisation & project kickoff | 50% |
| Milestone 2 | On 75% completion of Phase 1 | 25% |
| Milestone 3 | Phase 1 deliverables complete & client sign-off | 25% |

Phase 2 — Advanced Modules & Enhancements

| MILESTONE | DESCRIPTION | PAYMENT |
| --- | --- | --- |
| Milestone 1 | Phase 2 kickoff (post Phase 1 completion) | 50% |
| Milestone 2 | On 75% completion of Phase 2 | 25% |
| Milestone 3 | Phase 2 deliverables complete & client sign-off | 25% |

## 11.3  Key Notes

- Discovery includes requirement workshops, scope validation and architecture alignment.

- Kickoff begins after approval of the finalised scope.

- Each phase completion includes feature delivery as per agreed scope, UAT completion and formal client sign-off.

- Any additional scope is handled via a written change request with separate commercial approval.

- Third-party tools, integrations and infrastructure costs are borne by Kash Kids.

# 12. What's Included & Out of Scope

Included

- All modules listed in Phases 1 and 2, plus the value-added AI features

- Web platform and native mobile apps (iOS + Android)

- Deployment to your chosen cloud environment

- Admin and franchise training sessions plus written documentation

- Source code and IP transfer on final payment

- 90-day warranty and 30 days of free post-launch support

Out of Scope (billed separately if required)

- Cloud hosting, domain and third-party subscription costs

- Payment gateway transaction fees and SMS/WhatsApp/email gateway charges

- Content creation (course material, videos, marketing copy)

- Features not listed in this proposal, handled via change request

# 13. Assumptions

- Kash Kids will provide business workflows, sample data and validation inputs in a timely manner.

- Access to hosting infrastructure and required third-party accounts will be provided at kickoff.

- A single point of contact will be available for reviews, approvals and UAT sign-off.

- Scope changes follow the agreed change-request process.

# 14. Warranty & Support

- A 90-day warranty from go-live covering bug fixes and servicing at no cost.

- Minor issues during the warranty period are fixed free of charge.

- Major changes or new features during this period are scoped and agreed with a mutually accepted cost.

- Support beyond the warranty period is available under a separate Annual Maintenance Contract (AMC), priced on request.

# 15. Next Steps

- Confirm scope and commercials, and select single-phase or bundle engagement.

- Sign the agreement and raise the Milestone 1 invoice.

- Book the discovery workshop — we can start within one week of sign-off.

Let's build the system that runs your network. We're ready when you are.

MANAC INFOTECH

Kondal Reddy  ·  manacinliberty@gmail.com ·  www.manacinfotech.com