# PROPOSAL & COMMERCIAL QUOTATION

KNOWLEDGE HUB
PREMIUM EDUCATIONAL PLATFORM

Date: September 20, 2026
Prepared For: Knowledge Hub Management
Project Duration: 4 Weeks

# 1. Executive Summary & Objective

The objective of this project is to architect, design, and deploy a state-of-the-art digital educational platform for Knowledge Hub. Unlike traditional template-based websites, this platform is engineered as a high-performance Single Page Application (SPA). It is designed to maximize student engagement, automate lead generation, and provide a premium, interactive experience that sets Knowledge Hub apart from competitors.

# 2. Detailed Scope of Work & Deliverables

The project encompasses the complete development of the platform, including the following detailed features:

## A. Frontend Architecture & Global Features

• Responsive Design: Fully optimized for Mobile, Tablet, and Desktop displays using modern CSS Grid techniques.
• Single Page Application (SPA): Lightning-fast page transitions without browser reloads.
• Modern UI Aesthetics: Implementation of Glassmorphism, deep gradient shadowing, and Framer Motion micro-animations.
• AI Chatbot Assistant: A floating widget integrated with a custom-trained AI model that answers queries based on Knowledge Hub's specific curriculum and faculty data.

## B. Page-Specific Implementations

• Home Page: Cinematic hero section with orbiting technology animations, dynamic placement partners marquee, and featured course grids.
• About Us Page: Highly interactive 'Lab Simulator' UI demonstrating practical execution (CLI, Cloud, DAX, English). Includes 5-Step Journey Timelines, animated statistic counters, and dynamic curriculum domain tabs.
• Courses Directory: Advanced filtering system (by category/domain), detailed course cards, and comprehensive syllabus modals.
• Services Page: Specialized corporate training offerings and visually striking expert mentor profiles with skill tags.
• Contact Page: Interactive map integration and robust communication pipelines.

## C. Backend Database & Lead Generation

• Supabase Architecture: Secure, scalable PostgreSQL database integration.
• Automated Lead Capture: Seamless connection of all Enrolment, Contact, and Enquiry modals to the central database for CRM tracking.
• Data Integrity: Server-side validation to ensure clean, actionable lead data.

# 3. Proposed Technology Stack

• Frontend Framework: React.js (Vite) with TanStack Router for extreme performance.
• Styling & Animation: Tailwind CSS, Framer Motion, and Lucide Icons.
• Backend & Database: Supabase (PostgreSQL) for BaaS (Backend-as-a-Service).
• AI Integration: Custom logic mapped to LLM APIs for the intelligent chatbot.

# 4. Project Timeline (4 Weeks)

Week 1: UI/UX Finalization & Core Framework Setup
• Setup of React environment and routing architecture.
• Development of Global Components (Navigation, Footer, Typography).
• Delivery of the Home and Contact pages.

Week 2: Interactive Modules & Complex Animations
• Engineering the About Page (Lab Simulator, 5-Step Timeline).
• Construction of the Courses Directory and dynamic filtering.
• Implementation of mobile-specific layout optimizations.

Week 3: Backend Integration & Database Connectivity
• Supabase database schema design.
• Linking all UI modals (Enrolment, Enquiry) to the database.
• Testing data flow and lead capture integrity.

Week 4: AI Chatbot, QA Testing & Deployment
• Integration and training of the custom AI Chatbot.
• Cross-browser and cross-device Quality Assurance (QA) testing.
• Production build generation, SEO setup, and live server deployment.

# 5. Commercial Investment

Below is the detailed cost breakdown for the end-to-end development of the platform.

| Project Module | Investment (INR) |
| --- | --- |
| 1. Core SPA Architecture & UI/UX Design (Home, Contact, Services) | ₹ 75,000 |
| 2. Advanced Interactive Modules (Lab Simulators, Timelines, Grids) | ₹ 65,000 |
| 3. Dynamic Course Directory & Advanced Filtering Systems | ₹ 40,000 |
| 4. Supabase Backend Integration & Lead Generation System | ₹ 45,000 |
| 5. Custom AI Chatbot Development & Knowledge Training | ₹ 45,000 |
| 6. Server Deployment, SSL Setup & Technical SEO | ₹ 15,000 |
| Total Quoted Investment | ₹ 2,85,000 |

* Note: All costs are exclusive of domain registration, server hosting fees, and applicable taxes (GST).

# 6. Payment Milestones

• 30% Advance (₹ 85,500): Upon project initiation and contract signing.
• 40% Milestone (₹ 1,14,000): Upon completion of Week 2 (Frontend & Interactive Modules completed).
• 30% Final (₹ 85,500): Upon completion of Week 4, successful QA testing, and live deployment.

# 7. Acceptance & Authorization

By signing below, you authorize the commencement of this project based on the scope, timeline, and investment defined in this document.

___________________________________
Authorized Signature (Knowledge Hub)

___________________________________
Date